New Fire Station Cost Summary (Planning-Level Estimate)

For Inclusion in the CPCSD Fire Facilities Strategic Plan

1. Project Concept

A new CPCSD fire station modeled on the recently constructed Folsom Fire Station 34, incorporating:

- Approx. 12,195 sq. ft. facility (admin, dorms, dayroom, fitness room, support spaces).

- Three oversized apparatus bays capable of housing multiple engines and specialty units.

- Unfinished second floor shell for future dorm expansion (similar to Folsom).

- Contemporary construction: wood-frame, slab-on-grade, metal roofing, durable finishes.

- Full site improvements: secured yard, bio-swales, apparatus apron, parking, landscaping.

This size and programming supports a modern all-risk fire agency, future staffing growth, and improved operational performance.

2. Cost Basis

Planning-level cost model uses:

- RSMeans updated cost: $798.27 per sq. ft. (2025 dollars)

- Construction cost breakdown aligned with fire station project data.

- Localized Western U.S. cost adjustments from RSMeans.

- Folsom Station 34 cost/size as a validated regional comparator.

3. Hard Construction Cost

- Building Cost:
12,195 sq. ft. × $798.27 ≈ $9.7 million

- Site & Civil Improvements:
Grading, utilities, paving, stormwater, fencing, landscaping ≈ $1.9 million

Total Hard Construction: ≈ $11.6 million

4. Soft Costs (≈ 25% of Construction)

Includes architectural & engineering design, environmental/CEQA (if applicable), permits, plan check, testing & inspections, construction management, FF&E, and owner contingencies.

- Soft Cost Allowance: ≈ $2.9 million

5. Land Acquisition (3.0 Acres Assumed)

Based on comparable public-safety parcel valuations in the region.

- Planning Allowance:
$500,000 per acre × 3 acres = $1.5 million

(Range if desired: $1.05M–$2.25M depending on parcel characteristics.)

6. Total Project Budget (2025 Dollars)

| Cost Component | Estimated Cost |
| --- | --- |
| Hard Construction | $11.6M |
| Soft Costs | $2.9M |
| Land Acquisition (3 acres) | $1.5M |
| Total Estimated Cost | ≈ $16.0 million |

Planning Range:
$15.0M – $17.5M depending on final site conditions, escalation, and design choices.

7. Notes for Strategic Integration

- Costs do not include escalation beyond 2025; add 5–7% per year for planning to a 2028 bond cycle.

- Final scope validation (number of bays, future dorm capacity, presence of joint police space, training features, etc.) will refine the estimate.

- A new station aligns with CPCSD’s long-term operational strategy and integrates with expected operational revenue from the countywide “El Dorado Ready!” initiative, reducing future staffing-funding pressure.