## Cover
Cameron Park Community Services District
Five-Year Capital Improvement Program and Capital Asset Replacement Plan
FY 2026/27 through FY 2030/31
Board Adoption Draft
This rebuilt workbook separates true capital projects from operating maintenance, planning studies, completed projects, and removed items. Department totals reconcile to the Master CIP Register and summary schedules.

## Executive Dashboard
Executive Dashboard
Key Metrics |  |  | Active 5-Year CIP by Department
Active 5-Year CIP | 5389295.128 |  | Department | 5-Year CIP | Future CIP | Total
Future Capital Replacement | 13969224.4221 |  | Parks | 1653850 | 7150000 | 8803850
Total Capital Portfolio | 19358519.5501 |  | Fire Department | 401350 | 4275000 | 4676350
Maintenance Program (Operating) | 897200 |  | Community Center | 1105000 | 430000 | 1535000
Planning Studies (Operating) | 2040000 |  | Recreation | 413000 | 510000 | 923000
Completed/Historical | 99900 |  | LLAD | 95000 | 0 | 95000
Removed/Excluded | 8879600 |  | Equipment & Vehicle Replacement | 1721095.128 | 1604224.4221 | 3325319.5501
|  |  | TOTAL | 5389295.128 | 13969224.4221 | 19358519.5501
Top 10 High/Critical Capital Projects
CIP ID | Department | Project | Risk | Total
EQ-001 | Equipment & Vehicle Replacement | E88 - Type I WUI - Smeal Spartan | Critical | 1289224.4221
EQ-002 | Equipment & Vehicle Replacement | E89 - Type I WUI - Smeal Spartan | Critical | 1055878.803
PK-F05 | Parks | Complete Shoreline Stabilization Program | High | 750000
PK-F03 | Parks | Lake Outlet Structure Rehabilitation | High | 500000
CC-011 | Community Center | Resurface Pool | Critical | 455000
FD-F18 | Fire Department | SCBA Replacement Program | Critical | 450000
PK-F07 | Parks | Irrigation System Replacement | High | 400000
PK-F10 | Parks | Parking Lot Rehabilitation | High | 350000
PK-F21 | Parks | ADA Accessibility Improvement Program | High | 300000
PK-019 | Parks | Multi-Age Playground | High | 270000

## Master CIP Register
Cameron Park CSD - Master CIP Register (Capital Projects Only)
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-002 | Aquatics Center | Aquatics Center Shade (PYC FY25/26) | New Capital | High | 75000 | 97500 | 97500 | [5 empty] | Community Center Reserve / Grant | High | Patron comfort and UV protection
Community Center | 5-Year CIP | CC-003 | Aquatics Center | Aquatics Slide Replacement (PYC FY25/26) | New Capital | High | 125000 | 162500 | 162500 | [5 empty] | Community Center Reserve / Grant | High | End-of-life aquatic feature
Community Center | 5-Year CIP | CC-007 | Aquatics Center | Pool Deck Fence Maintenance (PYC FY25/26) | Replacement Capital | High | 30000 | 39000 | 39000 | [5 empty] | Facility Reserve | High | Multi-phase safety project
Community Center | 5-Year CIP | CC-011 | Aquatics Center | Resurface Pool | Replacement Capital | High | 350000 | 455000 | 455000 | [5 empty] | Community Center Reserve / Grant | Critical | Major pool preservation project
Community Center | 5-Year CIP | CC-005 | Community Center | Interior Lighting Panel (PYC FY25/26) | Replacement Capital | Medium | 25000 | 32500 | 32500 | [5 empty] | Facility Reserve | Moderate | Electrical system upgrade
Community Center | 5-Year CIP | CC-009 | Community Center | Resurface Gym & Hall Floors | Replacement Capital | Medium | 20000 | 26000 | 26000 | [5 empty] | Facility Reserve | Moderate | Extend facility life
Community Center | 5-Year CIP | CC-014 | Aquatics Center | Pool Deck Repairs | Replacement Capital | Medium | 100000 | 130000 |  | 130000 |  |  |  |  | Facility Reserve | High | Concrete and deck rehabilitation
Community Center | 5-Year CIP | CC-012 | Community Center | Repaint Main Exterior | Replacement Capital | Low | 50000 | 65000 | 65000 | [5 empty] | Facility Reserve | Moderate | Building envelope protection
Community Center | 5-Year CIP | CC-015 | Community Center | Resurface Main Hall | Replacement Capital | Low | 75000 | 97500 |  | 97500 |  |  |  |  | Facility Reserve | Low | Facility modernization
Community Center | 5-Year CIP | CC-034 | Aquatics Center | Pool Filtration System Upgrade | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Community Center Reserve | High | Long-term replacement need
Community Center | 5-Year CIP | CC-031 | Community Center | Wi-Fi & Technology Infrastructure Upgrade | Replacement Capital | Medium |  | 30000 | [5 empty] | 30000 | Technology Reserve | Moderate | Future service enhancement
Community Center | 5-Year CIP | CC-035 | Community Center | Emergency Generator Installation | New Capital | Medium |  | 250000 | [5 empty] | 250000 | FEMA Grant / Reserve | Moderate | Requires Board policy direction
Community Center | 5-Year CIP | CC-016 | Community Center | Refurbish Restrooms | Replacement Capital | Low | 100000 | 100000 |  |  | 0 |  |  |  | Facility Reserve / ADA Funding | High | Major restroom renovation
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-002 | Station 89 | E89 - Type I WUI - Smeal Spartan | Replacement Capital | Critical | 900000 | 1055878.803 |  |  |  |  | 1055878.803 |  | Fire Capital Replacement Fund / Development Fees | Critical | Owner Department: Fire Department; VIN: 457CT2D91FC079936; License: 1489217; Asset ID: 15-007; Service Life: 15 years; Replacement Year: 2030; Acquisition Year: 2015; Vehicle Year: 2015; Mileage: 90368; Annual Reserve Need: $46,168; Capital Replacement Fund Share: $776,071; Development Fee Share: $279,808
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-008 | Station 88 | U88 - Utility - Ford F-150 | Replacement Capital | High | 60000 | 47216.5126 | 47216.5126 | [5 empty] | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FTFX1EV8AFC17326; License: 1275431; Asset ID: 14-006; Service Life: 10 years; Replacement Year: 2020; Acquisition Year: 2010; Vehicle Year: 2010; Mileage: 78949; Annual Reserve Need: $3,219; Capital Replacement Fund Share: $34,704; Development Fee Share: $12,512
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-009 | Station 89 | U89 - Utility - Ford F-250 | Replacement Capital | High | 60000 | 67636.3125 |  |  |  | 67636.3125 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B63KEF56190; License: 1582183; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2010; Mileage: 73337; Annual Reserve Need: $4,611; Capital Replacement Fund Share: $49,713; Development Fee Share: $17,924
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-010 | Fire Department Command Fleet | B2715 - Utility - Ford F-250 | Replacement Capital | High | 80000 | 90181.75 |  |  |  | 90181.75 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B67KEF56189; License: 1582184; Asset ID: 19-008; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2019; Annual Reserve Need: $6,148; Capital Replacement Fund Share: $66,284; Development Fee Share: $23,898
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-011 | Fire Department Command Fleet | B2705 - Utility - Ford F-250 | Replacement Capital | High | 80000 | 90181.75 |  |  |  | 90181.75 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B63KEF56190; License: 1582183; Asset ID: 19-009; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2019; Annual Reserve Need: $6,148; Capital Replacement Fund Share: $66,284; Development Fee Share: $23,898
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-014 | Parks/Recreation/Administration Fleet | Truck #7 - Utility - Chevrolet 1500 | Replacement Capital | High | 50000 | 50000 |  | 50000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; Asset ID: 20-016; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2005; Annual Reserve Need: $4,982; Capital Replacement Fund Share: $36,750; Development Fee Share: $13,250
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-015 | Parks/Recreation/Administration Fleet | Truck #5 - Utility - Ford 2500 | Replacement Capital | High | 60000 | 60000 |  | 60000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 1FTNW2L91EB43557; Asset ID: 20-015; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2001; Annual Reserve Need: $5,979; Capital Replacement Fund Share: $44,100; Development Fee Share: $15,900; Notes: Has the only Liftgate
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-016 | Parks/Recreation/Administration Fleet | Truck #2 - Utility - Ford F-250 | Replacement Capital | High | 60000 | 60000 |  | 60000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; Asset ID: 20-012; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2002; Annual Reserve Need: $5,979; Capital Replacement Fund Share: $44,100; Development Fee Share: $15,900
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-017 | Parks/Recreation/Administration Fleet | Truck #3 - Utility - Ford F-150 | Replacement Capital | High | 45000 | 45000 |  | 45000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 1FTRF122X8KD02342; Asset ID: 20-013; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2008; Annual Reserve Need: $4,484; Capital Replacement Fund Share: $33,075; Development Fee Share: $11,925
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-018 | Parks/Recreation/Administration Fleet | Truck #4 - Utility - Dodge 3500 | Replacement Capital | High | 75000 | 75000 |  | 75000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 3B6MF3665YM229039; Asset ID: 20-014; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2000; Annual Reserve Need: $7,474; Capital Replacement Fund Share: $55,125; Development Fee Share: $19,875; Notes: Utility Body
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-019 | Parks/Recreation/Administration Fleet | Truck #8 - Utility - Ford Ranger | Replacement Capital | High | 40000 | 40000 |  | 40000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Facilities; VIN: 1FTYR11E58PA05108; Asset ID: 20-017; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2010; Annual Reserve Need: $3,986; Capital Replacement Fund Share: $29,400; Development Fee Share: $10,600
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-022 | Parks/Recreation/Administration Fleet | CC&R - Staff - Ford Taures | Replacement Capital | High | 35000 | 40000 |  | 40000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Administration; VIN: 1FAFP52UX4G139526; License: 1168632; Asset ID: CC&R; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2004; Vehicle Year: 2004; Mileage: 87844; Annual Reserve Need: $1,071; Capital Replacement Fund Share: $29,400; Development Fee Share: $10,600
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-001 | Station 88 | E88 - Type I WUI - Smeal Spartan | Replacement Capital | Critical | 900000 | 1289224.4221 | [5 empty] | 1289224.4221 | Fire Capital Replacement Fund / Development Fees | Critical | Owner Department: Fire Department; VIN: 4S9BEETA7LS419697; License: 1293085; Asset ID: 20-010; Service Life: 15 years; Replacement Year: 2035; Acquisition Year: 2020; Vehicle Year: 2020; Mileage: 46570; Annual Reserve Need: $58,672; Capital Replacement Fund Share: $986,257; Development Fee Share: $302,968
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-013 | Fire Department | Water Rescue Truck | Replacement Capital | Critical | 195000 | 250000 | [5 empty] | 250000 | Fire Capital Replacement Fund | Critical | Owner Department: Fire Department; Service Life: 15 years; Replacement Year: 2041; Vehicle Year: 2026
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-023 | Parks/Recreation/Administration Fleet | WFRC - Staff - Toyota bZ4X | Replacement Capital | Medium | 32000 | 40000 | [5 empty] | 40000 | Equipment Replacement Reserve | Moderate | Owner Department: Administration; VIN: JTMABACA1SA093746; License: 9TMB087; Asset ID: WFRC; Service Life: 15 years; Acquisition Year: 2025; Vehicle Year: 2025; Mileage: 5710
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-024 | Parks/Recreation Equipment | Dump - Trailer - BigTex 14LP | Replacement Capital | Low | 13000 | 13000 | [5 empty] | 13000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 20 years; Vehicle Year: 2020
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-027 | Parks/Recreation Equipment | eX-Mark Kawasaki 60" - Mower - eX-Mark | Replacement Capital | Low | 12000 | 12000 | [5 empty] | 12000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 7 years
Fire Department | 5-Year CIP | FD-012 | Both Stations | Replace SCBA Cylinders | Replacement Capital | High | 15000 | 21000 | 21000 | [5 empty] | Equipment Reserve | Critical | NFPA safety equipment
Fire Department | 5-Year CIP | FD-021 | Station 88 | Roof Replacement | Replacement Capital | High | 45000 | 60750 |  | 60750 |  |  |  |  | Capital Reserve | Critical | Full roof replacement
Fire Department | 5-Year CIP | FD-024 | Station 89 | Roof Replacement | Replacement Capital | High | 45000 | 60750 |  |  | 60750 |  |  |  | Capital Reserve | Critical | Full roof replacement
Fire Department | 5-Year CIP | FD-033 | Both Stations | Replace/Update Phone System | Replacement Capital | High | 0 | 35000 |  |  |  | 35000 |  |  | Technology Reserve | High | Communication system modernization
Fire Department | 5-Year CIP | FD-042 | Station 89 | Replace Barnco Building | Replacement Capital | High | 0 | 12500 |  |  | 12500 |  |  |  | Capital Reserve / Grant | HIgh | Replace aging auxiliary structure
Fire Department | 5-Year CIP | FD-001 | Station 89 | Front Apron Repair | Replacement Capital | Medium | 20000 | 27000 | 27000 | [5 empty] | Facilities Reserve | High | Concrete deterioration at apparatus access
Fire Department | 5-Year CIP | FD-018 | Station 89 | High-Speed Floor Burnisher | New Capital | Medium | 5000 | 7000 | 7000 | [5 empty] | Equipment Reserve | Low | Maintenance equipment
Fire Department | 5-Year CIP | FD-020 | Station 89 | Kitchen Appliance Replacement | Replacement Capital | Medium | 8000 | 11200 | 11200 | [5 empty] | Facilities Reserve | Moderate | Kitchen modernization
Fire Department | 5-Year CIP | FD-025 | Station 89 | Upgrade Convault | Replacement Capital | Medium | 10000 | 13500 |  |  | 13500 |  |  |  | Equipment Reserve | High | Fuel system improvements
Fire Department | 5-Year CIP | FD-032 | Both Stations | Replace Computers | Replacement Capital | Medium | 0 | 30000 |  |  |  | 30000 |  |  | Technology Reserve | Moderate | Computer replacement cycle
Fire Department | 5-Year CIP | FD-035 | Both Stations | Replace Toilets & Urinals | Replacement Capital | Medium | 0 | 18000 |  |  |  | 18000 |  |  | Facilities Reserve | Moderate | Low-flow fixture replacement
Fire Department | 5-Year CIP | FD-004 | Station 88 | Re-Surface Apparatus Floors | Replacement Capital | Low | 9000 | 12150 | 12150 | [5 empty] | Facilities Reserve | Moderate | Match Station 89 finish
Fire Department | 5-Year CIP | FD-027 | Station 89 | Replace Office Furniture | Replacement Capital | Low | 0 | 15000 |  |  |  | 15000 |  |  | Facilities Reserve | Low | Administrative workstations
Fire Department | 5-Year CIP | FD-028 | Station 89 | Replace BC/Prevention Furniture | Replacement Capital | Low | 0 | 10000 |  |  |  | 10000 |  |  | Facilities Reserve | Low | Prevention office furniture
Fire Department | 5-Year CIP | FD-040 | Station 89 | Install Metal Entry Gates | New Capital | Low | 50000 | 67500 |  |  |  |  | 67500 |  | Facilities Reserve | Moderate | Security enhancement
Fire Department | Future CIP | FD-F18 | Both Stations | SCBA Replacement Program | Replacement Capital | Critical | 0 | 450000 | [5 empty] | 450000 | Equipment Reserve / AFG Grant | Critical | Future SCBA unit replacement beyond cylinders
Fire Department | Future CIP | FD-F01 | Station 88 | HVAC Replacement | Replacement Capital | High | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | High | Existing HVAC recently replaced but future lifecycle replacement required
Fire Department | Future CIP | FD-F02 | Station 89 | HVAC Replacement | Replacement Capital | High | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | High | Future lifecycle replacement planning
Fire Department | Future CIP | FD-F03 | Station 88 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Backup power during PSPS and emergencies
Fire Department | Future CIP | FD-F04 | Station 89 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Station resiliency project
Fire Department | Future CIP | FD-F09 | Both Stations | Station Security Camera Upgrade | Replacement Capital | High | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Facility security and evidence retention
Fire Department | Future CIP | FD-F10 | Both Stations | Access Control System | New Capital | High | 0 | 40000 | [5 empty] | 40000 | Technology Reserve | Moderate | Electronic building access control
Fire Department | Future CIP | FD-F12 | Both Stations | Alerting System Modernization | Replacement Capital | High | 0 | 75000 | [5 empty] | 75000 | Grant / Technology Reserve | High | Station alerting and dispatch integration
Fire Department | Future CIP | FD-F13 | Station 88 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 80000 | [5 empty] | 80000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F14 | Station 89 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 120000 | [5 empty] | 120000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F17 | Station 89 | Fuel System Replacement | Replacement Capital | High | 0 | 250000 | [5 empty] | 250000 | Capital Reserve | High | Long-term replacement after Convault upgrades
Fire Department | Future CIP | FD-F05 | Both Stations | Solar & Battery Storage System | New Capital | Medium | 0 | 350000 | [5 empty] | 350000 | Grant / Reserve | Moderate | Energy resiliency and cost savings
Fire Department | Future CIP | FD-F06 | Station 88 | Dormitory Modernization | Replacement Capital | Medium | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | Moderate | Future firefighter housing improvements
Fire Department | Future CIP | FD-F07 | Station 89 | Dormitory Modernization | Replacement Capital | Medium | 0 | 200000 | [5 empty] | 200000 | Capital Reserve | Moderate | Modern sleeping quarters and finishes
Fire Department | Future CIP | FD-F08 | Station 89 | Kitchen & Dayroom Renovation | Replacement Capital | Medium | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | Moderate | Beyond cabinet replacement already planned
Fire Department | Future CIP | FD-F11 | Both Stations | Network Infrastructure Upgrade | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Future communications and data needs
Fire Department | Future CIP | FD-F15 | Station 88 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 75000 | [5 empty] | 75000 | Facilities Reserve | Moderate | Following current repair project
Fire Department | Future CIP | FD-F16 | Station 89 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 85000 | [5 empty] | 85000 | Facilities Reserve | Moderate | Energy efficiency improvements
Fire Department | Future CIP | FD-F19 | Both Stations | Fitness Equipment Replacement Program | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Facilities Reserve | Moderate | Replace gym equipment after current upgrades
Fire Department | Future CIP | FD-F22 | Districtwide | Fire Training Facility Development | New Capital | Medium | 0 | 1500000 | [5 empty] | 1500000 | Grant / Capital Reserve | Moderate | Long-term regional training facility
LLAD | 5-Year CIP | LLAD-007 | Districtwide | Lighting Replacement Program | Replacement Capital | High |  | 35000 |  |  |  |  | 35000 |  | LLAD Reserve | High | LED conversion and safety improvements
LLAD | 5-Year CIP | LLAD-004 | Eastwood Park | Irrigation Controller Replacement | Replacement Capital | Medium |  | 15000 |  | 15000 |  |  |  |  | LLAD Reserve | Moderate | Improve water efficiency
LLAD | 5-Year CIP | LLAD-005 | Northview Park | Landscape Renovation | Replacement Capital | Medium |  | 25000 |  |  | 25000 |  |  |  | LLAD Reserve | Low | Drought-tolerant conversion
LLAD | 5-Year CIP | LLAD-006 | Dave West Park | Pathway Rehabilitation | Replacement Capital | Medium |  | 20000 |  |  |  | 20000 |  |  | LLAD Reserve | Moderate | Asphalt and accessibility improvements
Parks | 5-Year CIP | PK-001 | Cameron Park Lake | Solar Powered Lake Aerators | Replacement Capital | High | 75000 | 85000 | 85000 | [5 empty] | Parks Reserve | High | Currently PG&E powered; aeration system upgrade
Parks | 5-Year CIP | PK-002 | Cameron Park Lake | Automate Metal Entrance Gate | New Capital | High | 40000 | 54000 | 54000 | [5 empty] | Parks Reserve | Moderate | Improves access control and security
Parks | 5-Year CIP | PK-003 | Cameron Park Lake | Repair Boat Launch | Replacement Capital | High | 27000 | 36500 | 36500 | [5 empty] | Parks Reserve | High | Existing deterioration and safety concerns
Parks | 5-Year CIP | PK-005 | Equipment | Replace Tractor | Replacement Capital | High | 60000 | 78000 | 78000 | [5 empty] | Equipment Reserve | High | End of useful life
Parks | 5-Year CIP | PK-012 | Cameron Park Lake | Replace Playground | Replacement Capital | High | 50000 | 67500 |  |  |  | 67500 |  |  | Parks Reserve / Grant | High | ADA and safety improvements
Parks | 5-Year CIP | PK-014 | Cameron Park Lake | Reinforce Culverts | Replacement Capital | High | 88000 | 118800 |  |  |  | 118800 |  |  | Parks Reserve | High | Infrastructure stabilization
Parks | 5-Year CIP | PK-015 | Cameron Park Lake | Repair East Inlet Bank | Replacement Capital | High | 20000 | 27000 |  |  |  | 27000 |  |  | Parks Reserve | High | Erosion control project
Parks | 5-Year CIP | PK-019 | Cameron Park Lake | Multi-Age Playground | New Capital | High | 200000 | 270000 |  |  |  |  | 270000 |  | Grant / Parks Reserve | High | New destination playground
Parks | 5-Year CIP | PK-004 | Cameron Park Lake | Tennis Court Repair | Replacement Capital | Medium | 75000 | 101250 | 101250 | [5 empty] | Parks Reserve / Grant | Moderate | Court resurfacing and crack repair
Parks | 5-Year CIP | PK-007 | Christa McAuliffe Park | Soccer Field Repair | Replacement Capital | Medium | 150000 | 150000 |  | 150000 |  |  |  |  | Grant / Reserve | High | Repair or Resod fields
Parks | 5-Year CIP | PK-008 | Cameron Park Lake | Replace Entry Signage | Replacement Capital | Medium | 50000 | 67500 |  |  | 67500 |  |  |  | Parks Reserve | Low | Wayfinding and entry improvements
Parks | 5-Year CIP | PK-009 | Cameron Park Lake | Replace Aging Docks | Replacement Capital | Medium | 100000 | 135000 |  |  | 135000 |  |  |  | Parks Reserve | Moderate | Aging infrastructure replacement
Parks | 5-Year CIP | PK-010 | Cameron Park Lake | Add Solar CATS | New Capital | Medium | 25000 | 32500 |  |  |  | 32500 |  |  | Grant / Reserve | Low | Additional lake aeration enhancements
Parks | 5-Year CIP | PK-011 | Cameron Park Lake | Replace Chain Link Fencing | Replacement Capital | Medium | 100000 | 135000 |  |  |  | 135000 |  |  | Parks Reserve | Moderate | Perimeter security and safety
Parks | 5-Year CIP | PK-016 | CP Lake, Christa & Rasmussen | Refurbish Restrooms | Replacement Capital | Medium | 50000 | 67500 |  |  |  | 67500 |  |  | Parks Reserve | Moderate | Multi-park restroom improvements
Parks | 5-Year CIP | PK-018 | Rasmussen Park | Repair Baseball Fields | Replacement Capital | Medium | 58000 | 78300 |  |  |  | 78300 |  |  | Parks Reserve | Moderate | Infield and irrigation improvements
Parks | 5-Year CIP | PK-021 | Christa McAuliffe Park | Pickleball Courts | New Capital | Medium | 500 | 150000 |  |  |  |  | 150000 |  | Grant / Reserve | Moderate | Original estimate appears understated; adjusted to realistic project cost
Parks | Future CIP | PK-F03 | Cameron Park Lake | Lake Outlet Structure Rehabilitation | Replacement Capital | High |  | 500000 | [5 empty] | 500000 | Grant / Reserve | High | Future water control infrastructure replacement
Parks | Future CIP | PK-F05 | Cameron Park Lake | Complete Shoreline Stabilization Program | Replacement Capital | High |  | 750000 | [5 empty] | 750000 | Grant / Reserve | High | Expands berm and bank stabilization efforts
Parks | Future CIP | PK-F07 | Cameron Park Lake | Irrigation System Replacement | Replacement Capital | High |  | 400000 | [5 empty] | 400000 | Parks Reserve | High | Aging irrigation infrastructure
Parks | Future CIP | PK-F10 | Cameron Park Lake | Parking Lot Rehabilitation | Replacement Capital | High |  | 350000 | [5 empty] | 350000 | Parks Reserve | High | Future pavement lifecycle replacement
Parks | Future CIP | PK-F11 | Christa McAuliffe Park | Sports Field Lighting | New Capital | High |  | 600000 | [5 empty] | 600000 | Grant / Reserve | Moderate | Expand evening recreation opportunities
Parks | Future CIP | PK-F20 | Districtwide | Irrigation Controller Modernization | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Water Efficiency Grants | Moderate | Smart irrigation and water conservation
Parks | Future CIP | PK-F21 | Districtwide | ADA Accessibility Improvement Program | New Capital | High |  | 300000 | [5 empty] | 300000 | ADA Grant / Reserve | High | Pathways, parking, playground access
Parks | Future CIP | PK-F04 | Cameron Park Lake | Fishing Pier Replacement | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term recreational asset replacement
Parks | Future CIP | PK-F06 | Cameron Park Lake | Lake Lighting Improvements | Replacement Capital | Medium |  | 150000 | [5 empty] | 150000 | Parks Reserve | Moderate | Public safety and security improvements
Parks | Future CIP | PK-F09 | Cameron Park Lake | Pavilion/Event Structure | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Sponsorships | Moderate | Revenue-generating event space
Parks | Future CIP | PK-F13 | Christa McAuliffe Park | Playground Replacement Cycle | Replacement Capital | Medium |  | 350000 | [5 empty] | 350000 | Parks Reserve | Moderate | Future replacement after useful life
Parks | Future CIP | PK-F14 | Rasmussen Park | Complete Trail System Rehabilitation | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term trail improvements
Parks | Future CIP | PK-F15 | Rasmussen Park | Sports Field Irrigation Replacement | Replacement Capital | Medium |  | 300000 | [5 empty] | 300000 | Parks Reserve | Moderate | Irrigation modernization
Parks | Future CIP | PK-F16 | Rasmussen Park | Field Lighting Installation | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Reserve | Moderate | Expand field use hours
Parks | Future CIP | PK-F17 | Paul J. Ryan Park | Park Rehabilitation Program | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Parks Reserve | Moderate | Future park asset upgrades
Parks | Future CIP | PK-F18 | Districtwide | Park Security Camera Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Parks Reserve | Moderate | Security and vandalism prevention
Parks | Future CIP | PK-F22 | Districtwide | Parks Maintenance Corporation Yard | Replacement Capital | Medium |  | 1500000 | [5 empty] | 1500000 | Capital Reserve | Moderate | Long-term operations facility
Recreation | 5-Year CIP | REC-003 | Aquatics Center | Inflatable/Moveable Pool Attraction | Replacement Capital | High |  | 40000 | 40000 | [5 empty] | Recreation Enterprise Revenue | High | Revenue-generating attraction
Recreation | 5-Year CIP | REC-004 | Aquatics Center | Lifeguard Training Equipment Package | Replacement Capital | High |  | 15000 | 15000 | [5 empty] | Recreation Budget | High | Updated rescue mannequins, infant mannequins, AED trainer and training equipment
Recreation | 5-Year CIP | REC-002 | Aquatics Center | Replace Diving Blocks | Replacement Capital | Medium |  | 18000 | 18000 | [5 empty] | Recreation Reserve | Moderate | Competition and swim team support
Recreation | 5-Year CIP | REC-010 | Aquatics Center | Shade Structure Expansion | New Capital | Medium |  | 75000 |  |  | 75000 |  |  |  | Grant / Recreation Reserve | Moderate | Additional spectator and patron shade
Recreation | 5-Year CIP | REC-011 | Aquatics Center | Pool Furniture Replacement Program | Replacement Capital | Medium |  | 25000 |  |  |  | 25000 |  |  | Recreation Reserve | Low | Tables, chairs, umbrellas and deck furnishings
Recreation | 5-Year CIP | REC-012 | Districtwide | Recreation Program Trailer & Event Equipment | New Capital | Medium |  | 35000 |  |  |  | 35000 |  |  | Recreation Reserve | Moderate | Supports special events and outreach
Recreation | 5-Year CIP | REC-001 | Aquatics Center | Pool Gate Kiosk System | New Capital | Low | 20000 | 25000 | 25000 | [5 empty] | Recreation Reserve | Low | Improves admissions and customer service
Recreation | 5-Year CIP | REC-008 | Aquatics Center | Electronic Scoreboard | New Capital | Low | 100000 | 130000 |  |  | 130000 |  |  |  | Recreation Reserve / Donations | Low | Swim meets and competitive programming
Recreation | 5-Year CIP | REC-014 | Aquatics Center | Swim Meet Timing System | New Capital | Low |  | 50000 |  |  |  |  | 50000 |  | Recreation Reserve / Sponsorships | Low | Competitive aquatics enhancement
Recreation | Future CIP | REC-F06 | Districtwide | Electronic Community Message Boards | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Sponsorships / Grants | Low | Community event and recreation marketing
Recreation | Future CIP | REC-F13 | Districtwide | Inclusive Recreation Equipment Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Grants | Moderate | ADA-inclusive recreation opportunities
Recreation | Future CIP | REC-F14 | Districtwide | Outdoor Fitness Stations | New Capital | Medium |  | 75000 | [5 empty] | 75000 | Health Grants | Low | Community wellness initiative
Recreation | Future CIP | REC-F18 | Districtwide | Recreation Equipment Replacement Reserve | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Recreation Reserve | Moderate | Long-term equipment replacement fund
Recreation | Future CIP | REC-F09 | Districtwide | Outdoor Movie & Event Equipment Package | Replacement Capital | Low |  | 35000 | [5 empty] | 35000 | Recreation Revenue | Low | Support community events
TOTAL | [6 empty] | 5142500 | 19458519.5501 | 1455816.5126 | 823250 | 519250 | 962599.8124 | 1628378.803 | 13969224.4221
Note on A1: Capital projects only. Maintenance, planning studies, completed projects, and removed items are excluded and retained in separate tabs for transparency.

## Parks
Parks Capital Improvement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Parks | 5-Year CIP | PK-001 | Cameron Park Lake | Solar Powered Lake Aerators | Replacement Capital | High | 75000 | 85000 | 85000 | [5 empty] | Parks Reserve | High | Currently PG&E powered; aeration system upgrade
Parks | 5-Year CIP | PK-002 | Cameron Park Lake | Automate Metal Entrance Gate | New Capital | High | 40000 | 54000 | 54000 | [5 empty] | Parks Reserve | Moderate | Improves access control and security
Parks | 5-Year CIP | PK-003 | Cameron Park Lake | Repair Boat Launch | Replacement Capital | High | 27000 | 36500 | 36500 | [5 empty] | Parks Reserve | High | Existing deterioration and safety concerns
Parks | 5-Year CIP | PK-005 | Equipment | Replace Tractor | Replacement Capital | High | 60000 | 78000 | 78000 | [5 empty] | Equipment Reserve | High | End of useful life
Parks | 5-Year CIP | PK-012 | Cameron Park Lake | Replace Playground | Replacement Capital | High | 50000 | 67500 |  |  |  | 67500 |  |  | Parks Reserve / Grant | High | ADA and safety improvements
Parks | 5-Year CIP | PK-014 | Cameron Park Lake | Reinforce Culverts | Replacement Capital | High | 88000 | 118800 |  |  |  | 118800 |  |  | Parks Reserve | High | Infrastructure stabilization
Parks | 5-Year CIP | PK-015 | Cameron Park Lake | Repair East Inlet Bank | Replacement Capital | High | 20000 | 27000 |  |  |  | 27000 |  |  | Parks Reserve | High | Erosion control project
Parks | 5-Year CIP | PK-019 | Cameron Park Lake | Multi-Age Playground | New Capital | High | 200000 | 270000 |  |  |  |  | 270000 |  | Grant / Parks Reserve | High | New destination playground
Parks | 5-Year CIP | PK-004 | Cameron Park Lake | Tennis Court Repair | Replacement Capital | Medium | 75000 | 101250 | 101250 | [5 empty] | Parks Reserve / Grant | Moderate | Court resurfacing and crack repair
Parks | 5-Year CIP | PK-007 | Christa McAuliffe Park | Soccer Field Repair | Replacement Capital | Medium | 150000 | 150000 |  | 150000 |  |  |  |  | Grant / Reserve | High | Repair or Resod fields
Parks | 5-Year CIP | PK-008 | Cameron Park Lake | Replace Entry Signage | Replacement Capital | Medium | 50000 | 67500 |  |  | 67500 |  |  |  | Parks Reserve | Low | Wayfinding and entry improvements
Parks | 5-Year CIP | PK-009 | Cameron Park Lake | Replace Aging Docks | Replacement Capital | Medium | 100000 | 135000 |  |  | 135000 |  |  |  | Parks Reserve | Moderate | Aging infrastructure replacement
Parks | 5-Year CIP | PK-010 | Cameron Park Lake | Add Solar CATS | New Capital | Medium | 25000 | 32500 |  |  |  | 32500 |  |  | Grant / Reserve | Low | Additional lake aeration enhancements
Parks | 5-Year CIP | PK-011 | Cameron Park Lake | Replace Chain Link Fencing | Replacement Capital | Medium | 100000 | 135000 |  |  |  | 135000 |  |  | Parks Reserve | Moderate | Perimeter security and safety
Parks | 5-Year CIP | PK-016 | CP Lake, Christa & Rasmussen | Refurbish Restrooms | Replacement Capital | Medium | 50000 | 67500 |  |  |  | 67500 |  |  | Parks Reserve | Moderate | Multi-park restroom improvements
Parks | 5-Year CIP | PK-018 | Rasmussen Park | Repair Baseball Fields | Replacement Capital | Medium | 58000 | 78300 |  |  |  | 78300 |  |  | Parks Reserve | Moderate | Infield and irrigation improvements
Parks | 5-Year CIP | PK-021 | Christa McAuliffe Park | Pickleball Courts | New Capital | Medium | 500 | 150000 |  |  |  |  | 150000 |  | Grant / Reserve | Moderate | Original estimate appears understated; adjusted to realistic project cost
Parks | Future CIP | PK-F03 | Cameron Park Lake | Lake Outlet Structure Rehabilitation | Replacement Capital | High |  | 500000 | [5 empty] | 500000 | Grant / Reserve | High | Future water control infrastructure replacement
Parks | Future CIP | PK-F05 | Cameron Park Lake | Complete Shoreline Stabilization Program | Replacement Capital | High |  | 750000 | [5 empty] | 750000 | Grant / Reserve | High | Expands berm and bank stabilization efforts
Parks | Future CIP | PK-F07 | Cameron Park Lake | Irrigation System Replacement | Replacement Capital | High |  | 400000 | [5 empty] | 400000 | Parks Reserve | High | Aging irrigation infrastructure
Parks | Future CIP | PK-F10 | Cameron Park Lake | Parking Lot Rehabilitation | Replacement Capital | High |  | 350000 | [5 empty] | 350000 | Parks Reserve | High | Future pavement lifecycle replacement
Parks | Future CIP | PK-F11 | Christa McAuliffe Park | Sports Field Lighting | New Capital | High |  | 600000 | [5 empty] | 600000 | Grant / Reserve | Moderate | Expand evening recreation opportunities
Parks | Future CIP | PK-F20 | Districtwide | Irrigation Controller Modernization | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Water Efficiency Grants | Moderate | Smart irrigation and water conservation
Parks | Future CIP | PK-F21 | Districtwide | ADA Accessibility Improvement Program | New Capital | High |  | 300000 | [5 empty] | 300000 | ADA Grant / Reserve | High | Pathways, parking, playground access
Parks | Future CIP | PK-F04 | Cameron Park Lake | Fishing Pier Replacement | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term recreational asset replacement
Parks | Future CIP | PK-F06 | Cameron Park Lake | Lake Lighting Improvements | Replacement Capital | Medium |  | 150000 | [5 empty] | 150000 | Parks Reserve | Moderate | Public safety and security improvements
Parks | Future CIP | PK-F09 | Cameron Park Lake | Pavilion/Event Structure | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Sponsorships | Moderate | Revenue-generating event space
Parks | Future CIP | PK-F13 | Christa McAuliffe Park | Playground Replacement Cycle | Replacement Capital | Medium |  | 350000 | [5 empty] | 350000 | Parks Reserve | Moderate | Future replacement after useful life
Parks | Future CIP | PK-F14 | Rasmussen Park | Complete Trail System Rehabilitation | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term trail improvements
Parks | Future CIP | PK-F15 | Rasmussen Park | Sports Field Irrigation Replacement | Replacement Capital | Medium |  | 300000 | [5 empty] | 300000 | Parks Reserve | Moderate | Irrigation modernization
Parks | Future CIP | PK-F16 | Rasmussen Park | Field Lighting Installation | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Reserve | Moderate | Expand field use hours
Parks | Future CIP | PK-F17 | Paul J. Ryan Park | Park Rehabilitation Program | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Parks Reserve | Moderate | Future park asset upgrades
Parks | Future CIP | PK-F18 | Districtwide | Park Security Camera Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Parks Reserve | Moderate | Security and vandalism prevention
Parks | Future CIP | PK-F22 | Districtwide | Parks Maintenance Corporation Yard | Replacement Capital | Medium |  | 1500000 | [5 empty] | 1500000 | Capital Reserve | Moderate | Long-term operations facility
TOTAL | [6 empty] | 1168500 | 8803850 | 354750 | 150000 | 202500 | 526600 | 420000 | 7150000

## Fire
Fire Department Capital Improvement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Fire Department | 5-Year CIP | FD-012 | Both Stations | Replace SCBA Cylinders | Replacement Capital | High | 15000 | 21000 | 21000 | [5 empty] | Equipment Reserve | Critical | NFPA safety equipment
Fire Department | 5-Year CIP | FD-021 | Station 88 | Roof Replacement | Replacement Capital | High | 45000 | 60750 |  | 60750 |  |  |  |  | Capital Reserve | Critical | Full roof replacement
Fire Department | 5-Year CIP | FD-024 | Station 89 | Roof Replacement | Replacement Capital | High | 45000 | 60750 |  |  | 60750 |  |  |  | Capital Reserve | Critical | Full roof replacement
Fire Department | 5-Year CIP | FD-033 | Both Stations | Replace/Update Phone System | Replacement Capital | High | 0 | 35000 |  |  |  | 35000 |  |  | Technology Reserve | High | Communication system modernization
Fire Department | 5-Year CIP | FD-042 | Station 89 | Replace Barnco Building | Replacement Capital | High | 0 | 12500 |  |  | 12500 |  |  |  | Capital Reserve / Grant | HIgh | Replace aging auxiliary structure
Fire Department | 5-Year CIP | FD-001 | Station 89 | Front Apron Repair | Replacement Capital | Medium | 20000 | 27000 | 27000 | [5 empty] | Facilities Reserve | High | Concrete deterioration at apparatus access
Fire Department | 5-Year CIP | FD-018 | Station 89 | High-Speed Floor Burnisher | New Capital | Medium | 5000 | 7000 | 7000 | [5 empty] | Equipment Reserve | Low | Maintenance equipment
Fire Department | 5-Year CIP | FD-020 | Station 89 | Kitchen Appliance Replacement | Replacement Capital | Medium | 8000 | 11200 | 11200 | [5 empty] | Facilities Reserve | Moderate | Kitchen modernization
Fire Department | 5-Year CIP | FD-025 | Station 89 | Upgrade Convault | Replacement Capital | Medium | 10000 | 13500 |  |  | 13500 |  |  |  | Equipment Reserve | High | Fuel system improvements
Fire Department | 5-Year CIP | FD-032 | Both Stations | Replace Computers | Replacement Capital | Medium | 0 | 30000 |  |  |  | 30000 |  |  | Technology Reserve | Moderate | Computer replacement cycle
Fire Department | 5-Year CIP | FD-035 | Both Stations | Replace Toilets & Urinals | Replacement Capital | Medium | 0 | 18000 |  |  |  | 18000 |  |  | Facilities Reserve | Moderate | Low-flow fixture replacement
Fire Department | 5-Year CIP | FD-004 | Station 88 | Re-Surface Apparatus Floors | Replacement Capital | Low | 9000 | 12150 | 12150 | [5 empty] | Facilities Reserve | Moderate | Match Station 89 finish
Fire Department | 5-Year CIP | FD-027 | Station 89 | Replace Office Furniture | Replacement Capital | Low | 0 | 15000 |  |  |  | 15000 |  |  | Facilities Reserve | Low | Administrative workstations
Fire Department | 5-Year CIP | FD-028 | Station 89 | Replace BC/Prevention Furniture | Replacement Capital | Low | 0 | 10000 |  |  |  | 10000 |  |  | Facilities Reserve | Low | Prevention office furniture
Fire Department | 5-Year CIP | FD-040 | Station 89 | Install Metal Entry Gates | New Capital | Low | 50000 | 67500 |  |  |  |  | 67500 |  | Facilities Reserve | Moderate | Security enhancement
Fire Department | Future CIP | FD-F18 | Both Stations | SCBA Replacement Program | Replacement Capital | Critical | 0 | 450000 | [5 empty] | 450000 | Equipment Reserve / AFG Grant | Critical | Future SCBA unit replacement beyond cylinders
Fire Department | Future CIP | FD-F01 | Station 88 | HVAC Replacement | Replacement Capital | High | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | High | Existing HVAC recently replaced but future lifecycle replacement required
Fire Department | Future CIP | FD-F02 | Station 89 | HVAC Replacement | Replacement Capital | High | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | High | Future lifecycle replacement planning
Fire Department | Future CIP | FD-F03 | Station 88 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Backup power during PSPS and emergencies
Fire Department | Future CIP | FD-F04 | Station 89 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Station resiliency project
Fire Department | Future CIP | FD-F09 | Both Stations | Station Security Camera Upgrade | Replacement Capital | High | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Facility security and evidence retention
Fire Department | Future CIP | FD-F10 | Both Stations | Access Control System | New Capital | High | 0 | 40000 | [5 empty] | 40000 | Technology Reserve | Moderate | Electronic building access control
Fire Department | Future CIP | FD-F12 | Both Stations | Alerting System Modernization | Replacement Capital | High | 0 | 75000 | [5 empty] | 75000 | Grant / Technology Reserve | High | Station alerting and dispatch integration
Fire Department | Future CIP | FD-F13 | Station 88 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 80000 | [5 empty] | 80000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F14 | Station 89 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 120000 | [5 empty] | 120000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F17 | Station 89 | Fuel System Replacement | Replacement Capital | High | 0 | 250000 | [5 empty] | 250000 | Capital Reserve | High | Long-term replacement after Convault upgrades
Fire Department | Future CIP | FD-F05 | Both Stations | Solar & Battery Storage System | New Capital | Medium | 0 | 350000 | [5 empty] | 350000 | Grant / Reserve | Moderate | Energy resiliency and cost savings
Fire Department | Future CIP | FD-F06 | Station 88 | Dormitory Modernization | Replacement Capital | Medium | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | Moderate | Future firefighter housing improvements
Fire Department | Future CIP | FD-F07 | Station 89 | Dormitory Modernization | Replacement Capital | Medium | 0 | 200000 | [5 empty] | 200000 | Capital Reserve | Moderate | Modern sleeping quarters and finishes
Fire Department | Future CIP | FD-F08 | Station 89 | Kitchen & Dayroom Renovation | Replacement Capital | Medium | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | Moderate | Beyond cabinet replacement already planned
Fire Department | Future CIP | FD-F11 | Both Stations | Network Infrastructure Upgrade | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Future communications and data needs
Fire Department | Future CIP | FD-F15 | Station 88 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 75000 | [5 empty] | 75000 | Facilities Reserve | Moderate | Following current repair project
Fire Department | Future CIP | FD-F16 | Station 89 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 85000 | [5 empty] | 85000 | Facilities Reserve | Moderate | Energy efficiency improvements
Fire Department | Future CIP | FD-F19 | Both Stations | Fitness Equipment Replacement Program | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Facilities Reserve | Moderate | Replace gym equipment after current upgrades
Fire Department | Future CIP | FD-F22 | Districtwide | Fire Training Facility Development | New Capital | Medium | 0 | 1500000 | [5 empty] | 1500000 | Grant / Capital Reserve | Moderate | Long-term regional training facility
TOTAL | [6 empty] | 207000 | 4676350 | 78350 | 60750 | 86750 | 108000 | 67500 | 4275000

## Community Center
Community Center Capital Improvement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-002 | Aquatics Center | Aquatics Center Shade (PYC FY25/26) | New Capital | High | 75000 | 97500 | 97500 | [5 empty] | Community Center Reserve / Grant | High | Patron comfort and UV protection
Community Center | 5-Year CIP | CC-003 | Aquatics Center | Aquatics Slide Replacement (PYC FY25/26) | New Capital | High | 125000 | 162500 | 162500 | [5 empty] | Community Center Reserve / Grant | High | End-of-life aquatic feature
Community Center | 5-Year CIP | CC-007 | Aquatics Center | Pool Deck Fence Maintenance (PYC FY25/26) | Replacement Capital | High | 30000 | 39000 | 39000 | [5 empty] | Facility Reserve | High | Multi-phase safety project
Community Center | 5-Year CIP | CC-011 | Aquatics Center | Resurface Pool | Replacement Capital | High | 350000 | 455000 | 455000 | [5 empty] | Community Center Reserve / Grant | Critical | Major pool preservation project
Community Center | 5-Year CIP | CC-005 | Community Center | Interior Lighting Panel (PYC FY25/26) | Replacement Capital | Medium | 25000 | 32500 | 32500 | [5 empty] | Facility Reserve | Moderate | Electrical system upgrade
Community Center | 5-Year CIP | CC-009 | Community Center | Resurface Gym & Hall Floors | Replacement Capital | Medium | 20000 | 26000 | 26000 | [5 empty] | Facility Reserve | Moderate | Extend facility life
Community Center | 5-Year CIP | CC-014 | Aquatics Center | Pool Deck Repairs | Replacement Capital | Medium | 100000 | 130000 |  | 130000 |  |  |  |  | Facility Reserve | High | Concrete and deck rehabilitation
Community Center | 5-Year CIP | CC-012 | Community Center | Repaint Main Exterior | Replacement Capital | Low | 50000 | 65000 | 65000 | [5 empty] | Facility Reserve | Moderate | Building envelope protection
Community Center | 5-Year CIP | CC-015 | Community Center | Resurface Main Hall | Replacement Capital | Low | 75000 | 97500 |  | 97500 |  |  |  |  | Facility Reserve | Low | Facility modernization
Community Center | 5-Year CIP | CC-034 | Aquatics Center | Pool Filtration System Upgrade | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Community Center Reserve | High | Long-term replacement need
Community Center | 5-Year CIP | CC-031 | Community Center | Wi-Fi & Technology Infrastructure Upgrade | Replacement Capital | Medium |  | 30000 | [5 empty] | 30000 | Technology Reserve | Moderate | Future service enhancement
Community Center | 5-Year CIP | CC-035 | Community Center | Emergency Generator Installation | New Capital | Medium |  | 250000 | [5 empty] | 250000 | FEMA Grant / Reserve | Moderate | Requires Board policy direction
Community Center | 5-Year CIP | CC-016 | Community Center | Refurbish Restrooms | Replacement Capital | Low | 100000 | 100000 |  |  | 0 |  |  |  | Facility Reserve / ADA Funding | High | Major restroom renovation
TOTAL | [6 empty] | 950000 | 1635000 | 877500 | 227500 | 0 | 0 | 0 | 430000

## Recreation
Recreation Capital Improvement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Recreation | 5-Year CIP | REC-003 | Aquatics Center | Inflatable/Moveable Pool Attraction | Replacement Capital | High |  | 40000 | 40000 | [5 empty] | Recreation Enterprise Revenue | High | Revenue-generating attraction
Recreation | 5-Year CIP | REC-004 | Aquatics Center | Lifeguard Training Equipment Package | Replacement Capital | High |  | 15000 | 15000 | [5 empty] | Recreation Budget | High | Updated rescue mannequins, infant mannequins, AED trainer and training equipment
Recreation | 5-Year CIP | REC-002 | Aquatics Center | Replace Diving Blocks | Replacement Capital | Medium |  | 18000 | 18000 | [5 empty] | Recreation Reserve | Moderate | Competition and swim team support
Recreation | 5-Year CIP | REC-010 | Aquatics Center | Shade Structure Expansion | New Capital | Medium |  | 75000 |  |  | 75000 |  |  |  | Grant / Recreation Reserve | Moderate | Additional spectator and patron shade
Recreation | 5-Year CIP | REC-011 | Aquatics Center | Pool Furniture Replacement Program | Replacement Capital | Medium |  | 25000 |  |  |  | 25000 |  |  | Recreation Reserve | Low | Tables, chairs, umbrellas and deck furnishings
Recreation | 5-Year CIP | REC-012 | Districtwide | Recreation Program Trailer & Event Equipment | New Capital | Medium |  | 35000 |  |  |  | 35000 |  |  | Recreation Reserve | Moderate | Supports special events and outreach
Recreation | 5-Year CIP | REC-001 | Aquatics Center | Pool Gate Kiosk System | New Capital | Low | 20000 | 25000 | 25000 | [5 empty] | Recreation Reserve | Low | Improves admissions and customer service
Recreation | 5-Year CIP | REC-008 | Aquatics Center | Electronic Scoreboard | New Capital | Low | 100000 | 130000 |  |  | 130000 |  |  |  | Recreation Reserve / Donations | Low | Swim meets and competitive programming
Recreation | 5-Year CIP | REC-014 | Aquatics Center | Swim Meet Timing System | New Capital | Low |  | 50000 |  |  |  |  | 50000 |  | Recreation Reserve / Sponsorships | Low | Competitive aquatics enhancement
Recreation | Future CIP | REC-F06 | Districtwide | Electronic Community Message Boards | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Sponsorships / Grants | Low | Community event and recreation marketing
Recreation | Future CIP | REC-F13 | Districtwide | Inclusive Recreation Equipment Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Grants | Moderate | ADA-inclusive recreation opportunities
Recreation | Future CIP | REC-F14 | Districtwide | Outdoor Fitness Stations | New Capital | Medium |  | 75000 | [5 empty] | 75000 | Health Grants | Low | Community wellness initiative
Recreation | Future CIP | REC-F18 | Districtwide | Recreation Equipment Replacement Reserve | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Recreation Reserve | Moderate | Long-term equipment replacement fund
Recreation | Future CIP | REC-F09 | Districtwide | Outdoor Movie & Event Equipment Package | Replacement Capital | Low |  | 35000 | [5 empty] | 35000 | Recreation Revenue | Low | Support community events
TOTAL | [6 empty] | 120000 | 923000 | 98000 | 0 | 205000 | 60000 | 50000 | 510000

## LLAD
LLAD Capital Improvement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
LLAD | 5-Year CIP | LLAD-007 | Districtwide | Lighting Replacement Program | Replacement Capital | High |  | 35000 |  |  |  |  | 35000 |  | LLAD Reserve | High | LED conversion and safety improvements
LLAD | 5-Year CIP | LLAD-004 | Eastwood Park | Irrigation Controller Replacement | Replacement Capital | Medium |  | 15000 |  | 15000 |  |  |  |  | LLAD Reserve | Moderate | Improve water efficiency
LLAD | 5-Year CIP | LLAD-005 | Northview Park | Landscape Renovation | Replacement Capital | Medium |  | 25000 |  |  | 25000 |  |  |  | LLAD Reserve | Low | Drought-tolerant conversion
LLAD | 5-Year CIP | LLAD-006 | Dave West Park | Pathway Rehabilitation | Replacement Capital | Medium |  | 20000 |  |  |  | 20000 |  |  | LLAD Reserve | Moderate | Asphalt and accessibility improvements
TOTAL | [6 empty] | 0 | 95000 | 0 | 15000 | 25000 | 20000 | 35000 | 0

## Equipment & Vehicle Replacement
Equipment & Vehicle Replacement Program
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-002 | Station 89 | E89 - Type I WUI - Smeal Spartan | Replacement Capital | Critical | 900000 | 1055878.803 |  |  |  |  | 1055878.803 |  | Fire Capital Replacement Fund / Development Fees | Critical | Owner Department: Fire Department; VIN: 457CT2D91FC079936; License: 1489217; Asset ID: 15-007; Service Life: 15 years; Replacement Year: 2030; Acquisition Year: 2015; Vehicle Year: 2015; Mileage: 90368; Annual Reserve Need: $46,168; Capital Replacement Fund Share: $776,071; Development Fee Share: $279,808
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-008 | Station 88 | U88 - Utility - Ford F-150 | Replacement Capital | High | 60000 | 47216.5126 | 47216.5126 | [5 empty] | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FTFX1EV8AFC17326; License: 1275431; Asset ID: 14-006; Service Life: 10 years; Replacement Year: 2020; Acquisition Year: 2010; Vehicle Year: 2010; Mileage: 78949; Annual Reserve Need: $3,219; Capital Replacement Fund Share: $34,704; Development Fee Share: $12,512
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-009 | Station 89 | U89 - Utility - Ford F-250 | Replacement Capital | High | 60000 | 67636.3125 |  |  |  | 67636.3125 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B63KEF56190; License: 1582183; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2010; Mileage: 73337; Annual Reserve Need: $4,611; Capital Replacement Fund Share: $49,713; Development Fee Share: $17,924
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-010 | Fire Department Command Fleet | B2715 - Utility - Ford F-250 | Replacement Capital | High | 80000 | 90181.75 |  |  |  | 90181.75 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B67KEF56189; License: 1582184; Asset ID: 19-008; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2019; Annual Reserve Need: $6,148; Capital Replacement Fund Share: $66,284; Development Fee Share: $23,898
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-011 | Fire Department Command Fleet | B2705 - Utility - Ford F-250 | Replacement Capital | High | 80000 | 90181.75 |  |  |  | 90181.75 |  |  | Fire Capital Replacement Fund / Development Fees | High | Owner Department: Fire Department; VIN: 1FT7W2B63KEF56190; License: 1582183; Asset ID: 19-009; Service Life: 10 years; Replacement Year: 2029; Acquisition Year: 2019; Vehicle Year: 2019; Annual Reserve Need: $6,148; Capital Replacement Fund Share: $66,284; Development Fee Share: $23,898
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-014 | Parks/Recreation/Administration Fleet | Truck #7 - Utility - Chevrolet 1500 | Replacement Capital | High | 50000 | 50000 |  | 50000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; Asset ID: 20-016; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2005; Annual Reserve Need: $4,982; Capital Replacement Fund Share: $36,750; Development Fee Share: $13,250
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-015 | Parks/Recreation/Administration Fleet | Truck #5 - Utility - Ford 2500 | Replacement Capital | High | 60000 | 60000 |  | 60000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 1FTNW2L91EB43557; Asset ID: 20-015; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2001; Annual Reserve Need: $5,979; Capital Replacement Fund Share: $44,100; Development Fee Share: $15,900; Notes: Has the only Liftgate
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-016 | Parks/Recreation/Administration Fleet | Truck #2 - Utility - Ford F-250 | Replacement Capital | High | 60000 | 60000 |  | 60000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; Asset ID: 20-012; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2002; Annual Reserve Need: $5,979; Capital Replacement Fund Share: $44,100; Development Fee Share: $15,900
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-017 | Parks/Recreation/Administration Fleet | Truck #3 - Utility - Ford F-150 | Replacement Capital | High | 45000 | 45000 |  | 45000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 1FTRF122X8KD02342; Asset ID: 20-013; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2008; Annual Reserve Need: $4,484; Capital Replacement Fund Share: $33,075; Development Fee Share: $11,925
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-018 | Parks/Recreation/Administration Fleet | Truck #4 - Utility - Dodge 3500 | Replacement Capital | High | 75000 | 75000 |  | 75000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Parks; VIN: 3B6MF3665YM229039; Asset ID: 20-014; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2000; Annual Reserve Need: $7,474; Capital Replacement Fund Share: $55,125; Development Fee Share: $19,875; Notes: Utility Body
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-019 | Parks/Recreation/Administration Fleet | Truck #8 - Utility - Ford Ranger | Replacement Capital | High | 40000 | 40000 |  | 40000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Facilities; VIN: 1FTYR11E58PA05108; Asset ID: 20-017; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2020; Vehicle Year: 2010; Annual Reserve Need: $3,986; Capital Replacement Fund Share: $29,400; Development Fee Share: $10,600
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-022 | Parks/Recreation/Administration Fleet | CC&R - Staff - Ford Taures | Replacement Capital | High | 35000 | 40000 |  | 40000 |  |  |  |  | Equipment Replacement Reserve / Development Fees | High | Owner Department: Administration; VIN: 1FAFP52UX4G139526; License: 1168632; Asset ID: CC&R; Service Life: 15 years; Replacement Year: 2027; Acquisition Year: 2004; Vehicle Year: 2004; Mileage: 87844; Annual Reserve Need: $1,071; Capital Replacement Fund Share: $29,400; Development Fee Share: $10,600
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-001 | Station 88 | E88 - Type I WUI - Smeal Spartan | Replacement Capital | Critical | 900000 | 1289224.4221 | [5 empty] | 1289224.4221 | Fire Capital Replacement Fund / Development Fees | Critical | Owner Department: Fire Department; VIN: 4S9BEETA7LS419697; License: 1293085; Asset ID: 20-010; Service Life: 15 years; Replacement Year: 2035; Acquisition Year: 2020; Vehicle Year: 2020; Mileage: 46570; Annual Reserve Need: $58,672; Capital Replacement Fund Share: $986,257; Development Fee Share: $302,968
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-013 | Fire Department | Water Rescue Truck | Replacement Capital | Critical | 195000 | 250000 | [5 empty] | 250000 | Fire Capital Replacement Fund | Critical | Owner Department: Fire Department; Service Life: 15 years; Replacement Year: 2041; Vehicle Year: 2026
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-023 | Parks/Recreation/Administration Fleet | WFRC - Staff - Toyota bZ4X | Replacement Capital | Medium | 32000 | 40000 | [5 empty] | 40000 | Equipment Replacement Reserve | Moderate | Owner Department: Administration; VIN: JTMABACA1SA093746; License: 9TMB087; Asset ID: WFRC; Service Life: 15 years; Acquisition Year: 2025; Vehicle Year: 2025; Mileage: 5710
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-024 | Parks/Recreation Equipment | Dump - Trailer - BigTex 14LP | Replacement Capital | Low | 13000 | 13000 | [5 empty] | 13000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 20 years; Vehicle Year: 2020
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-027 | Parks/Recreation Equipment | eX-Mark Kawasaki 60" - Mower - eX-Mark | Replacement Capital | Low | 12000 | 12000 | [5 empty] | 12000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 7 years
TOTAL | [6 empty] | 2697000 | 3325319.5501 | 47216.5126 | 370000 | 0 | 247999.8124 | 1055878.803 | 1604224.4221

## Maintenance Program
Maintenance Program - Excluded from Master CIP
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-001 | Community Center | Kitchen Roll-Up Door (PYC FY24/25) | Maintenance | Medium | 500 | 650 | 650 | [5 empty] | Facility Reserve | Low | Still needed
Community Center | 5-Year CIP | CC-006 | Community Center | Foyer Floors & Paint (PYC FY25/26) | Maintenance | Medium | 5000 | 6500 | 6500 | [5 empty] | Facility Reserve | Low | Cosmetic improvements
Community Center | 5-Year CIP | CC-008 | Aquatics Center | Pool Lights | Maintenance | Medium | 13000 | 16900 | 16900 | [5 empty] | Facility Reserve | Moderate | Safety and visibility
Community Center | 5-Year CIP | CC-017 | Community Center | Metal Roof Cap | Maintenance | Medium | 9000 | 11700 |  |  |  | 11700 |  |  | Facility Reserve | Moderate | Roof system protection
Fire Department | 5-Year CIP | FD-002 | Station 89 | Repair & Sealcoat Asphalt | Maintenance | Critical | 55000 | 74250 | 74250 | [5 empty] | Facilities Reserve | High | Prevents pavement failure
Fire Department | 5-Year CIP | FD-003 | Station 88 | Window Repairs | Maintenance | High | 12000 | 16200 | 16200 | [5 empty] | Facilities Reserve | High | Apparatus bay and kitchen windows
Fire Department | 5-Year CIP | FD-007 | Station 88 | Seal & Re-Stripe Asphalt | Maintenance | High | 4000 | 5400 | 5400 | [5 empty] | Facilities Reserve | Moderate | Asphalt preservation
Fire Department | 5-Year CIP | FD-015 | Station 88 | Exterior Brick Siding Repairs | Maintenance | High | 12000 | 15600 | 15600 | [5 empty] | Facilities Reserve | High | Building envelope protection
Fire Department | 5-Year CIP | FD-022 | Station 89 | Repair & Seal Asphalt | Maintenance | High | 5000 | 6750 |  | 6750 |  |  |  |  | Facilities Reserve | Moderate | Pavement preservation
Fire Department | 5-Year CIP | FD-031 | Station 89 | Fill Front Drainage Area | Maintenance | High | 0 | 35000 |  |  |  | 35000 |  |  | Facilities Reserve | High | Drainage correction
Fire Department | 5-Year CIP | FD-006 | Station 88 | Install Apparatus Bay Fan | Maintenance | Medium | 3000 | 3900 | 3900 | [5 empty] | Facilities Reserve | Moderate | Replace aging ventilation fan
Fire Department | 5-Year CIP | FD-008 | Station 89 | Paint Station Interior | Maintenance | Medium | 8000 | 10400 | 10400 | [5 empty] | Operating Budget | Low | Interior refresh
Fire Department | 5-Year CIP | FD-009 | Station 89 | Replace Door Openers | Maintenance | Medium | 3000 | 4200 | 4200 | [5 empty] | Equipment Reserve | Moderate | Three bay doors
Fire Department | 5-Year CIP | FD-013 | Station 89 | Re-Stain Fencing | Maintenance | Medium | 1000 | 1300 | 1300 | [5 empty] | Operating Budget | Low | Fence preservation
Fire Department | 5-Year CIP | FD-014 | Station 88 | Exterior Station Paint | Maintenance | Medium | 10000 | 13000 | 13000 | [5 empty] | Facilities Reserve | Moderate | Building exterior protection
Fire Department | 5-Year CIP | FD-017 | Station 88 | Replace Ice Machine | Maintenance | Medium | 4000 | 5600 | 5600 | [5 empty] | Equipment Reserve | Moderate | Kitchen equipment
Fire Department | 5-Year CIP | FD-019 | Station 89 | Update/Replace Gym Equipment | Maintenance | Medium | 8000 | 11200 | 11200 | [5 empty] | Facilities Reserve | Moderate | Firefighter wellness
Fire Department | 5-Year CIP | FD-023 | Station 89 | Install Apparatus Room Fan | Maintenance | Medium | 5000 | 6500 |  | 6500 |  |  |  |  | Facilities Reserve | Moderate | Ventilation upgrade
Fire Department | 5-Year CIP | FD-030 | Station 89 | Resurface Bay Room Floors | Maintenance | Medium | 0 | 27000 |  |  |  | 27000 |  |  | Facilities Reserve | Moderate | Apparatus bay restoration
Fire Department | 5-Year CIP | FD-036 | Station 89 | Replace Shower Tile Walls | Maintenance | Medium | 0 | 15000 |  |  |  | 15000 |  |  | Facilities Reserve | Moderate | Moisture protection
Fire Department | 5-Year CIP | FD-037 | Station 89 | Update Kitchen Cabinets | Maintenance | Medium | 0 | 20000 |  |  |  | 20000 |  |  | Facilities Reserve | Moderate | Kitchen modernization
Fire Department | 5-Year CIP | FD-038 | Station 89 | Replace Ice Machine | Maintenance | Medium | 0 | 8000 |  |  |  | 8000 |  |  | Equipment Reserve | Moderate | Commercial kitchen equipment
Fire Department | 5-Year CIP | FD-041 | Station 89 | Kitchenette/Laundry/Lobby Improvements | Maintenance | Medium | 7000 | 9100 |  |  |  |  | 9100 |  | Facilities Reserve | Low | Interior improvements
Fire Department | 5-Year CIP | FD-005 | Station 88 | Paint Apparatus Room Walls | Maintenance | Low | 4000 | 5200 | 5200 | [5 empty] | Operating Budget | Low | Interior maintenance
Fire Department | 5-Year CIP | FD-010 | Station 89 | Renovate Front Landscaping | Maintenance | Low | 2500 | 3250 | 3250 | [5 empty] | Operating Budget | Low | Site enhancement
Fire Department | 5-Year CIP | FD-011 | Station 89 | Renovate Rear Landscaping | Maintenance | Low | 2500 | 3250 | 3250 | [5 empty] | Operating Budget | Low | Site enhancement
Fire Department | 5-Year CIP | FD-016 | Station 88 | Replace Bed Frames & Mattresses | Maintenance | Low | 4000 | 5600 | 5600 | [5 empty] | Operating Budget | Low | Dormitory furnishings
Fire Department | 5-Year CIP | FD-026 | Station 88 | Replace Office Chairs | Maintenance | Low | 0 | 7000 |  |  |  | 7000 |  |  | Operating Budget | Low | Office furniture replacement
Fire Department | 5-Year CIP | FD-029 | Station 89 | Paint Apparatus Room Walls | Maintenance | Low | 0 | 10000 |  |  |  | 10000 |  |  | Operating Budget | Low | Interior maintenance
Fire Department | 5-Year CIP | FD-034 | Both Stations | Replace Blinds | Maintenance | Low | 0 | 6000 |  |  |  | 6000 |  |  | Operating Budget | Low | Interior improvements
Fire Department | 5-Year CIP | FD-039 | Both Stations | Replace BBQs | Maintenance | Low | 0 | 5000 |  |  |  | 5000 |  |  | Operating Budget | Low | Station support equipment
Parks | 5-Year CIP | PK-020 | Cameron Park Lake | Lake Wall Berm Repair | Maintenance | High | 300000 | 405000 |  |  |  |  | 405000 |  | Grant / Reserve | Critical | Structural shoreline stabilization
Parks | 5-Year CIP | PK-006 | Rasmussen Park | Repair Trail System | Maintenance | Medium | 20000 | 27000 | 27000 | [5 empty] | Parks Reserve | Moderate | Trail stabilization and erosion repair
Parks | 5-Year CIP | PK-013 | Cameron Park Lake | Remove Inlet Sediment | Maintenance | Medium | 40000 | 54000 |  |  |  | 54000 |  |  | Grant / Reserve | Moderate | Lake maintenance and water quality
Parks | 5-Year CIP | PK-017 | Paul J. Ryan Park | Install Culverts Along Back Path | Maintenance | Low | 5000 | 6750 |  |  |  | 6750 |  |  | Parks Reserve | Low | Drainage improvements
Recreation | 5-Year CIP | REC-005 | Aquatics Center | Improved Pool Deck Lighting | Maintenance | High | 20000 | 28000 | 28000 | [5 empty] | Recreation Reserve | High | Improves safety and evening operations
Recreation | 5-Year CIP | REC-006 | Aquatics Center | Updated Pool Safety Signage | Maintenance | Medium | 5000 | 7000 | 7000 | [5 empty] | Recreation Budget | Moderate | Regulatory and safety compliance
TOTAL | [6 empty] | 567500 | 897200 | 264400 | 13250 | 0 | 205450 | 414100 | 0

## Planning Studies
Planning Studies and Professional Services - Excluded from CIP
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-029 | Community Center | HVAC Replacement & Modernization Plan | Planning Study | High |  | 250000 | [5 empty] | 250000 | Facility Reserve | High | Pending facility assessment
Community Center | 5-Year CIP | CC-030 | Aquatics Center | Pool Mechanical Equipment Replacement | Planning Study | High |  | 250000 | [5 empty] | 250000 | Community Center Reserve | High | Pending mechanical assessment
Community Center | 5-Year CIP | CC-032 | Community Center | Roof Replacement Reserve Project | Planning Study | High |  | 500000 | [5 empty] | 500000 | Facility Reserve | Critical | Pending roof assessment
Community Center | 5-Year CIP | CC-033 | Community Center | Electrical Service Upgrade | Planning Study | High |  | 150000 | [5 empty] | 150000 | Facility Reserve | High | Assessment required
Fire Department | Future CIP | FD-F20 | Both Stations | Fire Station Condition Assessment & Reserve Study | Planning Study | High | 0 | 40000 | [5 empty] | 40000 | Facilities Reserve | High | Baseline for future capital planning
Fire Department | Future CIP | FD-F21 | Districtwide | Fire Training Prop / Training Tower Study | Planning Study | Medium | 0 | 75000 | [5 empty] | 75000 | Grant Funding | Moderate | Evaluate future firefighter training needs
Fire Department | Future CIP | FD-F23 | Station 88 | Station Expansion Feasibility Study | Planning Study | Medium | 0 | 50000 | [5 empty] | 50000 | Capital Reserve | Moderate | Evaluate future operational needs
Fire Department | Future CIP | FD-F24 | Station 89 | Station Expansion Feasibility Study | Planning Study | Medium | 0 | 50000 | [5 empty] | 50000 | Capital Reserve | Moderate | Evaluate future operational needs
Fire Department | Future CIP | FD-F25 | Districtwide | Future Fire Station #90 Feasibility Study | Planning Study | Medium | 0 | 100000 | [5 empty] | 100000 | Development Impact Fees | Moderate | Long-range service area planning
Parks | Future CIP | PK-F02 | Cameron Park Lake | Dam & Spillway Assessment | Planning Study | High |  | 100000 | [5 empty] | 100000 | Parks Reserve | High | Evaluate long-term structural integrity
Parks | Future CIP | PK-F24 | Districtwide | Parks Master Plan Update | Planning Study | High |  | 150000 | [5 empty] | 150000 | General Fund | Moderate | Long-range parks planning
Parks | Future CIP | PK-F25 | Districtwide | Future Community Park Acquisition Study | Planning Study | Medium |  | 250000 | [5 empty] | 250000
Recreation | Future CIP | REC-F05 | Aquatics Center | Aquatics Center Expansion Study | Planning Study | Medium |  | 75000 | [5 empty] | 75000 | Recreation Reserve | Moderate | Long-range aquatics planning
TOTAL | [6 empty] | 0 | 2040000 | 0 | 0 | 0 | 0 | 0 | 2040000

## Completed Projects
Completed / Historical Projects - Excluded from Active CIP
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-004 | Aquatics Center | Muriatic Acid Tank Replacement (PYC FY25/26) | Completed / Historical | High | 0 | 0 | 0 | [5 empty] | Existing Vendor | Moderate | Vendor providing replacement at no cost
Fire Department | Capital Replacement Plan | EQ-003 | Fire Department Fleet | E288 - Type I WUI - Smeal Spartan | Completed / Historical | Critical |  | 0 | 0 | [5 empty] | Fire Capital Replacement Fund | Critical | VIN: 457CT2D9X6CO54260; License: 1206288; Asset ID: 06-002; Service Life: 15 years; Replacement Year: 2021; Acquisition Year: 2006; Vehicle Year: 2006; Notes: This vhhicle was sold
LLAD | Completed/Historical | LLAD-001 | Eastwood Park | Concrete Expansion | Completed / Historical | High | 50000 | 67500 | 0 | [5 empty] | Fund Balance | Moderate | Completed project, retained for asset inventory
LLAD | Completed/Historical | LLAD-002 | Northview Park | Sound Wall Damage Repair | Completed / Historical | High | 17000 | 22950 | 0 | [5 empty] | Fund Balance | High | Completed project, protects adjacent properties
LLAD | Completed/Historical | LLAD-003 | Dave West Park | Repair Ballfield | Completed / Historical | Medium | 7000 | 9450 | 0 | [5 empty] | Prop 68 | Moderate | Field rehabilitation project
TOTAL | [6 empty] | 74000 | 99900 | 0 | 0 | 0 | 0 | 0 | 0

## Removed Projects
Removed / Excluded Projects - Audit Trail
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-010 | Community Center | Partitions | Removed / Excluded | Medium | 75000 | 97500 | 97500 | [5 empty] | Facility Reserve | Moderate | In progress
Community Center | 5-Year CIP | CC-013 | Aquatics Center | Old Pool Pump Refurbishment | Removed / Excluded | Low | 7000 | 9100 | 9100 | [5 empty] | Equipment Reserve | Low | Backup pump due to obsolete equipment
Community Center | 5-Year CIP | CC-018 | Aquatics Center | CO2 Expansion System | Removed / Excluded | Medium | 10000 | 13000 |  |  |  | 13000 |  |  | Facility Reserve | Moderate | Pool chemical automation / capacity expansion
Community Center | 5-Year CIP | CC-036 | Community Center | Audio/Visual System Upgrade | Removed / Excluded | Medium |  | 75000 | [5 empty] | 75000 | Technology Reserve | Moderate | Revenue enhancement project
Fire Department | Capital Replacement Plan | EQ-004 | Fire Department Fleet | E289 - Type I WUI - Smeal Spartan | Removed / Excluded | Critical |  | 0 | 0 | [5 empty] | Fire Capital Replacement Fund | Critical | VIN: 4S7CT2D936C054259; License: 1206287; Asset ID: 06-003; Service Life: 15 years; Replacement Year: 2021; Acquisition Year: 2006; Vehicle Year: 2006
Fire Department | Capital Replacement Plan | EQ-005 | Fire Department Fleet | E389 - Type III - HME Master | Removed / Excluded | Critical |  | 0 | 0 | [5 empty] | Fire Capital Replacement Fund | Critical | Asset ID: 01-001; Service Life: 15 years; Replacement Year: 2016; Acquisition Year: 2001; Vehicle Year: 2002
Fire Department | Capital Replacement Plan | EQ-006 | Fire Department Fleet | E388 - Type III - HME Navistar | Removed / Excluded | Critical |  | 0 | 0 | [5 empty] | Fire Capital Replacement Fund | Critical | VIN: 1HTWEAZR4CJ565999; License: 1375275; Asset ID: 11-005; Service Life: 15 years; Replacement Year: 2026; Acquisition Year: 2011; Vehicle Year: 2011
Fire Department | Capital Replacement Plan | EQ-007 | Fire Department Fleet | New E389 - Type III - BME Model 34 | Removed / Excluded | Critical |  | 0 | [5 empty] | 0 | Fire Capital Replacement Fund | Critical | Asset ID: 26-011; Service Life: 15 years; Replacement Year: 2039; Acquisition Year: 2024; Vehicle Year: 2027; Notes: New Vehicle, Will need to be added when it arrives
Fire Department | Capital Replacement Plan | EQ-012 | Fire Department | U289 - Utility - Ford F-250 | Removed / Excluded | High | [8 empty] | Fire Capital Replacement Fund | High | VIN: 1FTFW1EV2AFC17325; License: 1275433; Asset ID: 10-004; Service Life: 10 years; Replacement Year: 2020; Acquisition Year: 2010; Vehicle Year: 2010; Mileage: 154732
Parks | Capital Replacement Plan | EQ-020 | Parks/Recreation/Administration Fleet | Truck #1 - Utility - Ford | Removed / Excluded | Low | [8 empty] | Equipment Replacement Reserve | Low | VIN: 1FTBF2A64FEB14486; Asset ID: 20-018; Vehicle Year: 2015
Parks | Capital Replacement Plan | EQ-021 | Parks/Recreation/Administration Fleet | Truck #6 - Utility - Ford F-250 | Removed / Excluded | Low | [8 empty] | Equipment Replacement Reserve | Low | VIN: 1FTBF2A63JEC59026; Vehicle Year: 2018
Parks | Capital Replacement Plan | EQ-025 | Parks/Recreation Equipment | Black - Trailer | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 20 years
Parks | Capital Replacement Plan | EQ-026 | Parks/Recreation Equipment | Blue - Trailer | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 20 years
Parks | Capital Replacement Plan | EQ-028 | Parks/Recreation Equipment | Kawasaki Lazer 60" - Mower - Kawasaki Lazer | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 7 years; Vehicle Year: 2001
Parks | Capital Replacement Plan | EQ-029 | Parks/Recreation Equipment | eX-Mark Kohler 60" - Mower - eX-Mark | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 7 years
Parks | Capital Replacement Plan | EQ-030 | Parks/Recreation Equipment | Ranger - SidexSide - Polaris Ranger 570 | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 10 years; Vehicle Year: 2019
Parks | Capital Replacement Plan | EQ-031 | Parks/Recreation Equipment | Workman - SidexSide - Toro Workman | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 10 years
Parks | Capital Replacement Plan | EQ-032 | Parks/Recreation Equipment | Golf Cart - Golfcart - Yamaha G11A | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 10 years; Vehicle Year: 2000
Parks | Capital Replacement Plan | EQ-033 | Parks/Recreation Equipment | Tractor - Massey Ferguson MF1533 | Removed / Excluded | Low | [8 empty] | Capital Replacement Reserve | Low | Asset ID: PARKS; Service Life: 20 years
Parks | Future CIP | PK-F01 | Cameron Park Lake | Lake Dredging Program | Removed / Excluded | Critical |  | 2500000 | [5 empty] | 2500000 | Grant / Reserve | Critical | Long-term sediment removal and lake preservation
Parks | Future CIP | PK-F08 | Cameron Park Lake | Restroom Replacement Facility | Removed / Excluded | High |  | 750000 | [5 empty] | 750000 | Grant / Reserve | High | Replace aging restroom building
Parks | Future CIP | PK-F12 | Christa McAuliffe Park | Additional Sports Fields | Removed / Excluded | Medium |  | 1000000 | [5 empty] | 1000000 | Grant / Development Fees | Moderate | Future recreation demand
Parks | Future CIP | PK-F19 | Districtwide | LED Park Lighting Conversion | Removed / Excluded | Medium |  | 250000 | [5 empty] | 250000 | Energy Grant / Reserve | Moderate | Energy efficiency improvements
Parks | Future CIP | PK-F23 | Districtwide | Parks Equipment Replacement Program | Removed / Excluded | High |  | 500000 | [5 empty] | 500000 | Equipment Reserve | High | Mowers, utility vehicles, maintenance equipment
Recreation | 5-Year CIP | REC-007 | Districtwide | Digital Park Information Kiosks | Removed / Excluded | Medium |  | 45000 |  | 45000 |  |  |  |  | Recreation Reserve / Sponsorships | Moderate | Community information and event promotion
Recreation | 5-Year CIP | REC-009 | Districtwide | Recreation Asset Inventory & Technology Assessment | Removed / Excluded | Medium |  | 15000 | 15000 | [5 empty] | Recreation Budget | Moderate | Establish equipment replacement schedules
Recreation | 5-Year CIP | REC-013 | Districtwide | Mobile Recreation Check-In & Registration Technology | Removed / Excluded | Medium |  | 20000 |  |  |  |  | 20000 |  | Recreation Budget | Moderate | Supports remote events and programs
Recreation | Future CIP | REC-F01 | Aquatics Center | Splash Pad Feasibility Study | Removed / Excluded | Medium |  | 50000 | [5 empty] | 50000 | Grant / Recreation Reserve | Low | Evaluate future family aquatic attraction
Recreation | Future CIP | REC-F02 | Aquatics Center | Permanent Shade Pavilion | Removed / Excluded | Medium |  | 250000 | [5 empty] | 250000 | Grant / Donations | Moderate | Expand patron and spectator comfort
Recreation | Future CIP | REC-F03 | Aquatics Center | Additional Water Play Features | Removed / Excluded | Medium |  | 200000 | [5 empty] | 200000 | Recreation Revenue | Moderate | Increase attendance and programming opportunities
Recreation | Future CIP | REC-F04 | Aquatics Center | Competition Timing System | Removed / Excluded | Medium |  | 75000 | [5 empty] | 75000 | Recreation Reserve | Low | Supports swim meets and competitions
Recreation | Future CIP | REC-F07 | Districtwide | Recreation Storage Building | Removed / Excluded | Medium |  | 150000 | [5 empty] | 150000 | Recreation Reserve | Moderate | Secure storage for recreation equipment
Recreation | Future CIP | REC-F08 | Districtwide | Mobile Recreation Trailer | Removed / Excluded | Medium |  | 80000 | [5 empty] | 80000 | Recreation Reserve | Moderate | Expand outreach programming
Recreation | Future CIP | REC-F10 | Community Center | Recreation Technology Hub | Removed / Excluded | Medium |  | 150000 | [5 empty] | 150000 | Grants / Partnerships | Moderate | Youth and technology programming space
Recreation | Future CIP | REC-F11 | Aquatics Center | Additional Shade Structures | Removed / Excluded | Medium |  | 125000 | [5 empty] | 125000 | Grant Funding | Low | Expand pool deck shade coverage
Recreation | Future CIP | REC-F12 | Aquatics Center | Lazy River Feasibility Study | Removed / Excluded | Low |  | 75000 | [5 empty] | 75000 | Recreation Reserve | Low | Evaluate future aquatic amenity
Recreation | Future CIP | REC-F15 | Districtwide | Recreation Vehicle Replacement Program | Removed / Excluded | Medium |  | 100000 | [5 empty] | 100000 | Equipment Reserve | Moderate | Support recreation operations
Recreation | Future CIP | REC-F16 | Aquatics Center | Splash Pad Construction | Removed / Excluded | Low |  | 1200000 | [5 empty] | 1200000 | Grant / Measure Funding | Low | Future major aquatics expansion
Recreation | Future CIP | REC-F17 | Community Center | Outdoor Event Pavilion | Removed / Excluded | Medium |  | 350000 | [5 empty] | 350000 | Grants / Sponsorships | Moderate | Revenue-generating event venue
Recreation | Future CIP | REC-F19 | Aquatics Center | Pool Deck Expansion | Removed / Excluded | Low |  | 300000 | [5 empty] | 300000 | Recreation Reserve | Low | Future facility enhancement
Recreation | Future CIP | REC-F20 | Districtwide | Recreation Maintenance Facility | Removed / Excluded | Medium |  | 500000 | [5 empty] | 500000 | Capital Reserve | Moderate | Dedicated recreation operations facility
TOTAL | [6 empty] | 92000 | 8879600 | 121600 | 45000 | 0 | 13000 | 20000 | 8680000

## Capital Funding Plan
Capital Funding Plan by Funding Source
Funding Source | 5-Year CIP | Future CIP | Total
ADA Grant / Reserve | 0 | 300000 | 300000
Capital Replacement Reserve | 0 | 25000 | 25000
Capital Reserve | 121500 | 2500000 | 2621500
Capital Reserve / Grant | 12500 | 0 | 12500
Community Center Reserve | 0 | 150000 | 150000
Community Center Reserve / Grant | 715000 | 0 | 715000
Equipment Replacement Reserve | 0 | 40000 | 40000
Equipment Replacement Reserve / Development Fees | 370000 | 0 | 370000
Equipment Reserve | 119500 | 0 | 119500
Equipment Reserve / AFG Grant | 0 | 450000 | 450000
FEMA Grant / Reserve | 0 | 600000 | 600000
Facilities Reserve | 160850 | 410000 | 570850
Facility Reserve | 390000 | 0 | 390000
Facility Reserve / ADA Funding | 0 | 0 | 0
Fire Capital Replacement Fund | 0 | 250000 | 250000
Fire Capital Replacement Fund / Development Fees | 1351095.128 | 1289224.4221 | 2640319.5501
Grant / Capital Reserve | 0 | 1500000 | 1500000
Grant / Parks Reserve | 270000 | 0 | 270000
Grant / Recreation Reserve | 75000 | 0 | 75000
Grant / Reserve | 332500 | 2700000 | 3032500
Grant / Sponsorships | 0 | 500000 | 500000
Grant / Technology Reserve | 0 | 75000 | 75000
Grants | 0 | 100000 | 100000
Health Grants | 0 | 75000 | 75000
LLAD Reserve | 95000 | 0 | 95000
Parks Reserve | 804600 | 2350000 | 3154600
Parks Reserve / Grant | 168750 | 0 | 168750
Recreation Budget | 15000 | 0 | 15000
Recreation Enterprise Revenue | 40000 | 0 | 40000
Recreation Reserve | 103000 | 200000 | 303000
Recreation Reserve / Donations | 130000 | 0 | 130000
Recreation Reserve / Sponsorships | 50000 | 0 | 50000
Recreation Revenue | 0 | 35000 | 35000
Sponsorships / Grants | 0 | 100000 | 100000
Technology Reserve | 65000 | 170000 | 235000
Water Efficiency Grants | 0 | 150000 | 150000

## Five-Year Cash Flow
Five-Year CIP Cash Flow by Department
Department | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Total 5-Year CIP
Parks | 354750 | 150000 | 202500 | 526600 | 420000 | 1653850
Fire Department | 78350 | 60750 | 86750 | 108000 | 67500 | 401350
Community Center | 877500 | 227500 | 0 | 0 | 0 | 1105000
Recreation | 98000 | 0 | 205000 | 60000 | 50000 | 413000
LLAD | 0 | 15000 | 25000 | 20000 | 35000 | 95000
Equipment & Vehicle Replacement | 47216.5126 | 370000 | 0 | 247999.8124 | 1055878.803 | 1721095.128
TOTAL | 1455816.5126 | 823250 | 519250 | 962599.8124 | 1628378.803 | 5389295.128

## Capital Project Type Summary
Capital Project Type Summary
Capital Project Type | Project Count | 5-Year CIP | Future CIP | Total
New Capital | 27 | 1156000 | 4765000 | 5921000
Replacement Capital | 90 | 4233295.128 | 9204224.4221 | 13437519.5501

## Deferred Maintenance Summary
Deferred Maintenance / Replacement Capital Summary
Department | Replacement Capital - 5 Year | Replacement Capital - Future | Operating Maintenance Items | Total Preservation Need
Parks | 1147350 | 5150000 | 492750 | 6790100
Fire Department | 326850 | 2035000 | 333700 | 2695550
Community Center | 845000 | 180000 | 35750 | 1060750
Recreation | 98000 | 235000 | 35000 | 368000
LLAD | 95000 | 0 | 0 | 95000
Equipment & Vehicle Replacement | 1721095.128 | 1604224.4221 | 0 | 3325319.5501

## Future Capital Replacement
Future Capital Replacement Needs
Department | Program Type | CIP ID | Location / Asset Location | Project / Asset | Capital Project Type | Priority | Original Cost / Purchase Price | Current Cost Estimate / Replacement Cost | FY26/27 | FY27/28 | FY28/29 | FY29/30 | FY30/31 | Future CIP | Funding Source | Risk Rating | Comments / Replacement Detail
Community Center | 5-Year CIP | CC-034 | Aquatics Center | Pool Filtration System Upgrade | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Community Center Reserve | High | Long-term replacement need
Community Center | 5-Year CIP | CC-031 | Community Center | Wi-Fi & Technology Infrastructure Upgrade | Replacement Capital | Medium |  | 30000 | [5 empty] | 30000 | Technology Reserve | Moderate | Future service enhancement
Community Center | 5-Year CIP | CC-035 | Community Center | Emergency Generator Installation | New Capital | Medium |  | 250000 | [5 empty] | 250000 | FEMA Grant / Reserve | Moderate | Requires Board policy direction
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-001 | Station 88 | E88 - Type I WUI - Smeal Spartan | Replacement Capital | Critical | 900000 | 1289224.4221 | [5 empty] | 1289224.4221 | Fire Capital Replacement Fund / Development Fees | Critical | Owner Department: Fire Department; VIN: 4S9BEETA7LS419697; License: 1293085; Asset ID: 20-010; Service Life: 15 years; Replacement Year: 2035; Acquisition Year: 2020; Vehicle Year: 2020; Mileage: 46570; Annual Reserve Need: $58,672; Capital Replacement Fund Share: $986,257; Development Fee Share: $302,968
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-013 | Fire Department | Water Rescue Truck | Replacement Capital | Critical | 195000 | 250000 | [5 empty] | 250000 | Fire Capital Replacement Fund | Critical | Owner Department: Fire Department; Service Life: 15 years; Replacement Year: 2041; Vehicle Year: 2026
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-023 | Parks/Recreation/Administration Fleet | WFRC - Staff - Toyota bZ4X | Replacement Capital | Medium | 32000 | 40000 | [5 empty] | 40000 | Equipment Replacement Reserve | Moderate | Owner Department: Administration; VIN: JTMABACA1SA093746; License: 9TMB087; Asset ID: WFRC; Service Life: 15 years; Acquisition Year: 2025; Vehicle Year: 2025; Mileage: 5710
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-024 | Parks/Recreation Equipment | Dump - Trailer - BigTex 14LP | Replacement Capital | Low | 13000 | 13000 | [5 empty] | 13000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 20 years; Vehicle Year: 2020
Equipment & Vehicle Replacement | Capital Replacement Plan | EQ-027 | Parks/Recreation Equipment | eX-Mark Kawasaki 60" - Mower - eX-Mark | Replacement Capital | Low | 12000 | 12000 | [5 empty] | 12000 | Capital Replacement Reserve | Low | Owner Department: Parks; Asset ID: PARKS; Service Life: 7 years
Fire Department | Future CIP | FD-F18 | Both Stations | SCBA Replacement Program | Replacement Capital | Critical | 0 | 450000 | [5 empty] | 450000 | Equipment Reserve / AFG Grant | Critical | Future SCBA unit replacement beyond cylinders
Fire Department | Future CIP | FD-F01 | Station 88 | HVAC Replacement | Replacement Capital | High | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | High | Existing HVAC recently replaced but future lifecycle replacement required
Fire Department | Future CIP | FD-F02 | Station 89 | HVAC Replacement | Replacement Capital | High | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | High | Future lifecycle replacement planning
Fire Department | Future CIP | FD-F03 | Station 88 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Backup power during PSPS and emergencies
Fire Department | Future CIP | FD-F04 | Station 89 | Emergency Generator Installation | New Capital | High | 0 | 175000 | [5 empty] | 175000 | FEMA Grant / Reserve | High | Station resiliency project
Fire Department | Future CIP | FD-F09 | Both Stations | Station Security Camera Upgrade | Replacement Capital | High | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Facility security and evidence retention
Fire Department | Future CIP | FD-F10 | Both Stations | Access Control System | New Capital | High | 0 | 40000 | [5 empty] | 40000 | Technology Reserve | Moderate | Electronic building access control
Fire Department | Future CIP | FD-F12 | Both Stations | Alerting System Modernization | Replacement Capital | High | 0 | 75000 | [5 empty] | 75000 | Grant / Technology Reserve | High | Station alerting and dispatch integration
Fire Department | Future CIP | FD-F13 | Station 88 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 80000 | [5 empty] | 80000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F14 | Station 89 | Apparatus Bay Door Replacement | Replacement Capital | High | 0 | 120000 | [5 empty] | 120000 | Facilities Reserve | High | Full bay door replacement cycle
Fire Department | Future CIP | FD-F17 | Station 89 | Fuel System Replacement | Replacement Capital | High | 0 | 250000 | [5 empty] | 250000 | Capital Reserve | High | Long-term replacement after Convault upgrades
Fire Department | Future CIP | FD-F05 | Both Stations | Solar & Battery Storage System | New Capital | Medium | 0 | 350000 | [5 empty] | 350000 | Grant / Reserve | Moderate | Energy resiliency and cost savings
Fire Department | Future CIP | FD-F06 | Station 88 | Dormitory Modernization | Replacement Capital | Medium | 0 | 150000 | [5 empty] | 150000 | Capital Reserve | Moderate | Future firefighter housing improvements
Fire Department | Future CIP | FD-F07 | Station 89 | Dormitory Modernization | Replacement Capital | Medium | 0 | 200000 | [5 empty] | 200000 | Capital Reserve | Moderate | Modern sleeping quarters and finishes
Fire Department | Future CIP | FD-F08 | Station 89 | Kitchen & Dayroom Renovation | Replacement Capital | Medium | 0 | 125000 | [5 empty] | 125000 | Capital Reserve | Moderate | Beyond cabinet replacement already planned
Fire Department | Future CIP | FD-F11 | Both Stations | Network Infrastructure Upgrade | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Technology Reserve | Moderate | Future communications and data needs
Fire Department | Future CIP | FD-F15 | Station 88 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 75000 | [5 empty] | 75000 | Facilities Reserve | Moderate | Following current repair project
Fire Department | Future CIP | FD-F16 | Station 89 | Exterior Window Replacement Program | Replacement Capital | Medium | 0 | 85000 | [5 empty] | 85000 | Facilities Reserve | Moderate | Energy efficiency improvements
Fire Department | Future CIP | FD-F19 | Both Stations | Fitness Equipment Replacement Program | Replacement Capital | Medium | 0 | 50000 | [5 empty] | 50000 | Facilities Reserve | Moderate | Replace gym equipment after current upgrades
Fire Department | Future CIP | FD-F22 | Districtwide | Fire Training Facility Development | New Capital | Medium | 0 | 1500000 | [5 empty] | 1500000 | Grant / Capital Reserve | Moderate | Long-term regional training facility
Parks | Future CIP | PK-F03 | Cameron Park Lake | Lake Outlet Structure Rehabilitation | Replacement Capital | High |  | 500000 | [5 empty] | 500000 | Grant / Reserve | High | Future water control infrastructure replacement
Parks | Future CIP | PK-F05 | Cameron Park Lake | Complete Shoreline Stabilization Program | Replacement Capital | High |  | 750000 | [5 empty] | 750000 | Grant / Reserve | High | Expands berm and bank stabilization efforts
Parks | Future CIP | PK-F07 | Cameron Park Lake | Irrigation System Replacement | Replacement Capital | High |  | 400000 | [5 empty] | 400000 | Parks Reserve | High | Aging irrigation infrastructure
Parks | Future CIP | PK-F10 | Cameron Park Lake | Parking Lot Rehabilitation | Replacement Capital | High |  | 350000 | [5 empty] | 350000 | Parks Reserve | High | Future pavement lifecycle replacement
Parks | Future CIP | PK-F11 | Christa McAuliffe Park | Sports Field Lighting | New Capital | High |  | 600000 | [5 empty] | 600000 | Grant / Reserve | Moderate | Expand evening recreation opportunities
Parks | Future CIP | PK-F20 | Districtwide | Irrigation Controller Modernization | Replacement Capital | High |  | 150000 | [5 empty] | 150000 | Water Efficiency Grants | Moderate | Smart irrigation and water conservation
Parks | Future CIP | PK-F21 | Districtwide | ADA Accessibility Improvement Program | New Capital | High |  | 300000 | [5 empty] | 300000 | ADA Grant / Reserve | High | Pathways, parking, playground access
Parks | Future CIP | PK-F04 | Cameron Park Lake | Fishing Pier Replacement | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term recreational asset replacement
Parks | Future CIP | PK-F06 | Cameron Park Lake | Lake Lighting Improvements | Replacement Capital | Medium |  | 150000 | [5 empty] | 150000 | Parks Reserve | Moderate | Public safety and security improvements
Parks | Future CIP | PK-F09 | Cameron Park Lake | Pavilion/Event Structure | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Sponsorships | Moderate | Revenue-generating event space
Parks | Future CIP | PK-F13 | Christa McAuliffe Park | Playground Replacement Cycle | Replacement Capital | Medium |  | 350000 | [5 empty] | 350000 | Parks Reserve | Moderate | Future replacement after useful life
Parks | Future CIP | PK-F14 | Rasmussen Park | Complete Trail System Rehabilitation | Replacement Capital | Medium |  | 250000 | [5 empty] | 250000 | Parks Reserve | Moderate | Long-term trail improvements
Parks | Future CIP | PK-F15 | Rasmussen Park | Sports Field Irrigation Replacement | Replacement Capital | Medium |  | 300000 | [5 empty] | 300000 | Parks Reserve | Moderate | Irrigation modernization
Parks | Future CIP | PK-F16 | Rasmussen Park | Field Lighting Installation | New Capital | Medium |  | 500000 | [5 empty] | 500000 | Grant / Reserve | Moderate | Expand field use hours
Parks | Future CIP | PK-F17 | Paul J. Ryan Park | Park Rehabilitation Program | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Parks Reserve | Moderate | Future park asset upgrades
Parks | Future CIP | PK-F18 | Districtwide | Park Security Camera Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Parks Reserve | Moderate | Security and vandalism prevention
Parks | Future CIP | PK-F22 | Districtwide | Parks Maintenance Corporation Yard | Replacement Capital | Medium |  | 1500000 | [5 empty] | 1500000 | Capital Reserve | Moderate | Long-term operations facility
Recreation | Future CIP | REC-F06 | Districtwide | Electronic Community Message Boards | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Sponsorships / Grants | Low | Community event and recreation marketing
Recreation | Future CIP | REC-F13 | Districtwide | Inclusive Recreation Equipment Program | New Capital | Medium |  | 100000 | [5 empty] | 100000 | Grants | Moderate | ADA-inclusive recreation opportunities
Recreation | Future CIP | REC-F14 | Districtwide | Outdoor Fitness Stations | New Capital | Medium |  | 75000 | [5 empty] | 75000 | Health Grants | Low | Community wellness initiative
Recreation | Future CIP | REC-F18 | Districtwide | Recreation Equipment Replacement Reserve | Replacement Capital | Medium |  | 200000 | [5 empty] | 200000 | Recreation Reserve | Moderate | Long-term equipment replacement fund
Recreation | Future CIP | REC-F09 | Districtwide | Outdoor Movie & Event Equipment Package | Replacement Capital | Low |  | 35000 | [5 empty] | 35000 | Recreation Revenue | Low | Support community events
TOTAL | [6 empty] | 1152000 | 13969224.4221 | 0 | 0 | 0 | 0 | 0 | 13969224.4221